## Milestone Summary
Milestone | Critical Path Tasks | Task Group | Task Duration (Days) | Target Date
1 | Evaluate Market | Market Assessment | 12 | 27-04-2017
| Develop Business Opportunity |  | 14
| Customer Preference Study |  | 21
| Business Evaluation (NPV, etc.) |  | 4
2 | Design and Development Plan | Design | 6 | 06-06-2017
| Design Specifications |  | 22
3 | Advertising Campaign | Commercialization | 28 | 14-07-2017
4 | Design Labeling | Design | 5 | 03-08-2017
| Approve Design |  | 4
| Initial Engineering Specifications | Engineering | 5
5 | Design Verification Activities | Engineering | 7 | 01-09-2017
| Verification Design Review |  | 4
| Release Pre-production Specifications |  | 10
6 | Build Functional Model | Engineering | 18 | 27-09-2017
7 | Issue Sample (Production Equivalent) | Procurement | 5 | 24-10-2017
| Perform Supplier Process Capability | Supplier Quality | 14
8 | Process Engineering Plan | Manufacturing | 15 | 14-11-2017
9 | Validation Design Review | Engineering | 4 | 24-11-2017
| Approve Model Design |  | 4
10 | Qualify Supplier | Supplier Quality | 10 | 08-12-2017
| Design Transfer Activities | Engineering | 7
| Product Release Meetings | Engineering Quality | 3
11 | Develop Production Control Plan | Manufacturing | 8.5 | 08-01-2018
| Approve Production Parts |  | 5
| Contracting for Deliveries |  | 8
12 | Submit Production Purchase Order | Manufacturing | 2 | 31-01-2018
| Production Pilot Test |  | 5
| Debugging Production System |  | 4
| Production Release |  | 3
| Product Launch | Commercialization | 3